## Sheet1
Ben's Personal Log
Date | Start Time | Stop Time | Difference | Description
2011-03-29 | 12:15 | 13:15 | 1:00 | Develop WIA I.S.A. Process
2011-03-31 | 12:15 | 13:00 | 0:45 | Develop simple project plan
2011-04-05 | 12:15 | 13:15 | 1:00 | Begin creating uml class diagrams
2011-04-07 | 12:15 | 13:00 | 0:45 | Finished first round of class and first sequence diagrams
2011-04-10 | 15:00 | 16:30 | 1:30 | Convert whiteboard to visio diagrams
2011-04-12 | 12:15 | 14:45 | 2:30 | Completed several sequence diagrams
2011-04-14 | 12:15 | 13:15 | 1:00 | Setup git repository, assigned coding tasks
2011-04-15 | 20:00 | 22:45 | 2:45 | Created Pose and Point classes, tested, and committed.
2011-04-16 | 13:00 | 18:45 | 5:45 | Created object class, tested, and committed. Began external documentation using doxygen.
2011-04-18 | 10:45 | 12:00 | 1:15 | Created tank, and rendertype classes, tested, and committed.
2011-04-19 | 12:15 | 13:15 | 1:00 | Setup testdriver.cpp to allow for sandboxing of indivual code. Renamed RenderType to RenderObject.
2011-04-19 | 20:45 | 26:35 | 5:50 | Created RenderTypes.xml, RenderEngine, added xmlParser(tinyxml), tested and committed.
2011-04-20 | 22:00 | 23:50 | 1:50 | Updated cs325graphics class to latest release, created userinput class to capture user pressed keys.
2011-04-22 | 16:00 | 22:00 | 6:00 | added move and rotate methods to RenderEngine, tested successfully, commited changes
2011-04-26 | 12:00 | 23:00 | 11:00 | Updated game class. Created battlezone driver. Attempted to help Aaron implement collision detection with no success. Reverted back to only being able to navigate thru a randomly generated 3d world. Tested code that we have. Updated all documentation. Generated Final external documentation. Submitted project to moodle.
43:55